## Sheet1
Summer Research Schedule (Bora Basyildiz)
Week Num | Start Date | End Date | Tasks |  |  |  | Description | Objectives
1 | May 30th | June 6th | 1.1,1.2,1.3 | 2.1 |  |  | Planning and Intro Week | 1. Singularity | 2. Code | 3. Geometries
2 | June 6th | June 13th | 1.3 cont. | 2.3 | 3.1 | 3.1.1 | Parameters & Ring (Circle) BSI | 1.1 Read Paper | 2.1 Fix Singularity | 3.1 Ring (Circle)
3 | June 13th | June 20th |  |  | 3.1 | 3.1.2, 3.1.3 | Ring (Circle) kB & expansion | 1.2 Biot Savart Eq | 2.2 Hasimoto Div. | 3.2 Ring (Ellipse)
4 | June 20th | June 27th |  |  | 3.2 | 3.2.1, 3.2.2, 3.2.3 | Ring (Ellipse) all plots | 1.3 Set of Symbols | 2.3 Parameters | 3.3 Rough Ring
5 | June 27th | July 4th |  |  | 3.3 | 3.3.1 | Rough Ring BSI | 1.4 Write Paper | 2.4 Bending Energy | 3.4 Hasimoto Soliton
6 | July 4th | July 11th |  |  | 3.3 | 3.3.2, 3.3.3 | Rough Ring kB & expansion |  | 2.5 Curvature plots | 3.5 Ring With Soliton
7 | July 11th | July 18th |  |  | 3.4 | 3.4.1, 3.4.2, 3.4.3 | Hasimoto Soliton (all schemes)
8 | July 18th | July 25th |  | 2.4,2.5 |  |  | Bending Energy & Curvature plots | Geometries
9 | July 25th | Aug 1st | 1.4 |  |  |  | Writing Paper | 3.1 Ring (Circle) | 3.2 Ring (Ellipse) | 3.3 Rough Ring | 3.4 Hasimoto Soliton | 3.5 Ring With Soliton
10 | Aug 1st | Aug 8th | 1.4 |  |  |  | Writing Paper cont. | 3.1.1 BSI | 3.2.1 BSI | 3.3.1 BSI | 3.4.1 BSI | 3.5.1 BSI
11 | Aug 8th | Aug 15th |  |  | 3.5? | 3.5.1? | Extra week for delays & ring w/sol. | 3.1.2 kB | 3.2.2 kB | 3.3.2 kB | 3.4.2 kB | 3.5.2 kB
[8 empty] | 3.1.3 kB expansion | 3.2.3 kB expansion | 3.3.3 kB expansion | 3.4.3 kB expansion | 3.5.3 kB expansion